## Task Tracking Sheet
TravelMate
Date | Abhishek | Aartiben | Dhara | Hetvi
2024-03-01 | - Searched for the website name ideas and finalized one. | - Downloaded the Images for the website. | - Searched for the logo ideas according to the name of the site and finalized the design for the logo. | - Searched for the content for travel destination around the world.
2024-03-02 | - Created Folder structure and added JS, CSS and HTML files. | - Searched for the Content of the website such as Quotes, Slogans. | - Created the logo and made some changes in the logo and searched for the images to put it on the wesite. | - Worked on cards and added CSS to it.
2024-03-03 |  |  |  | - Worked on the cards for location images and descriptions.
2024-03-04 | - Worked on the Nav bar and animations for the Hamburger menu and added.
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10 | Worked on changing the look of home page. | Worked on service page , decided design for it | search for contact us page design and finalized the design of contact us | Worked on About Us webpage of website and created its wireframe. Also made responsive design for webpage.
2024-03-11 | Worked on changes in animation of nav links open from humbergar menu | create basic structure of hotel service(accomodation) page. | Find images for home pages | Added Details about company and decided design and layout of webpage.
2024-03-12 | Worked on home page background image on header section and also searched and added content on home page. | downloaded images for the hotel page of the service. | Start coding of contact us page | Created cards for destinations in the webpage and modified CSS page.
2024-03-13 | Started working on cards for popular locations. | started coding for hotel page. | For the contact us page,create contact form and do some changes | Added Feedback form in About Us Webpage.
2024-03-14 | Worked on responsive design for the cards and images for popular location div. | add and made some changes on hotel page. | add contact info and map on contact us page | Edited the webpage.
2024-03-15 | Worked on animation on hover and also changes in the design of cards and worked on css for the same. Completed background and popular locations divs. Created media query for the navbar and popular locations divs. | for the hotel page, create a sidebar and made changes in desiinging to look more responsive. | Working on css for contact us page | Added detailes about our team member in cards.
2024-03-16 | Worked on Home page popular locations enhancements in design. | started coding for package page in service page. | completed work on contact us page | Added an image and set headings on image in webpage
2024-03-17 | Started working on finding images for service and edited them in Canva, and started with services page designs. | worked on package page , made the changes on it. | search for registration and login form design and finally decice design for both | Added imformation about the company and made card for its imformation.
2024-03-18 | Completed services div and started working on extra info div | did the styling of the package page to look responsive | started coding for registration form | Worked on form for newsletter
2024-03-19 | Worked on extra info div and complete its design. | completed work on service page, which includes two pages. | work on CSS for registration form | Worked on CSS of webpage and collected images to use for website
2024-03-20 | Worked on testimonial div for customer reviews and statement. | apply the same design of the project theme to pages. | started coding for login form | added images and worked in layout of webpge.
2024-03-21 | Worked on design for testimonials and completed responsive design for all the previous sections.Worked on NewsLetter section. | made sitemap of the project | completed responsive design for both login and registration form | Worked on webpage to make it responsive.
2024-03-22 | Started working on compilation and final changes for other pages of the site. | did some changes in the site map and correct the mistake. | Stared working on Packages form | Had a look at all the sections ans website in order to answer the question
2024-03-23 | started working on the About Us page. | add another page in service page and decide the design of packages page. | Find images for packages pages | Completed all the answer of section - 1
2024-03-24 | Worked on About us page and completed designing part. | completed the designing. | did some changes in the contact us page | Started working on wireframes
2024-03-25 | Worked on responsive design of about us page and started working on compiling other pages. | did work on the styles of the webpage. | working on packages page | Wireframes of Mobile, Tablet and Desktop completed
2024-03-26 | Worked on fixing the design issues on all other pages. | made changes on the packages webpage | did some changes in the packages page | Worked on sitemap of the website
2024-03-27 | Worked on compiling and adding common sections and also common css in all other pages. | corrects the errors with the help of other groupmate the packages page responsive. | made packages page responsive with the help of other groupmate | Made changes in webpages by looking at sections
2024-03-28 | Worked on contact us page CSS changes and added background in login and contact us with black screen. | made the packages page responsive and complete the work. | completed work on packages page | Alter wireframes and made final changes
2024-03-29 | Worked on changing the folder structure and searched for the new name and logo for the website and added logo and favicon in the website and changed the tiles of the each page in the project. | made minor changes in the pages with the help of checklist and added them. | did some changes in pdf of section1 question answer | Alter SiteMap and made final changes
2024-03-30 | Worked on changing the CSS in the packages page and also did R&D for some of the flex property for integration.
2024-03-31 | worked on checking the pages and made necessary changes.Worked on changing the sitemaps and wireframes submitted by teammate. Also work on final bug fixing and changes.